## Blatt1
Timeplan | [7 empty] | Milestones
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag | Abbreviant | Artifact
Date | 2015-02-17 | 2015-02-18 | 2015-02-19 | 2015-02-20 | 2015-02-21 | 2015-02-22 | 2015-02-23 | MS01 | Project Plan / Timeplan
Morning |  | School | - | Research / reading | Research / reading | Free | Free | MS02 | Requirements / Mockups
Afternoon | School | School | Meeting Sarven | Research / reading | Research / reading | Free | Free | MS03 | Backend Developed
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag | MS04 | UI Developed
Date | 2015-02-23 | 2015-02-24 | 2015-02-25 | 2015-02-26 | 2015-02-27 | 2015-02-28 | 2015-03-01 | MS05 | Written Doc are online
Morning | Blog / MS01 | School | Wordpress setup | Wordpress setup | Requirements Engineering | Free | Free | MS06 | User Tests have been made
Afternoon | School | School | Wordpress setup | Wordpress setup | Requirements Engineering | Free | Free | MS07 | Prototype is ready
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag | MS08 | Finished BT
Date | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-05 | 2015-03-06 | 2015-03-07 | 2015-03-08 | MS09 | Abstract Uploaded on Moodle
Morning | MS02 | School | Design | Design | Design | Free | Free | MS10 | Presentation (Date to come)
Afternoon | School | School | Design | Design | Design | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-03-09 | 2015-03-10 | 2015-03-11 | 2015-03-12 | 2015-03-13 | 2015-03-14 | 2015-03-15
Morning | Recap | School | Development Backend | Development Backend | Development Backend | Free | Free
Afternoon | School | School | Development Backend | Development Backend | Development Backend | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-03-16 | 2015-03-17 | 2015-03-18 | 2015-03-19 | 2015-03-20 | 2015-03-21 | 2015-03-22
Morning | Blog | School | Development Backend | Development Backend | Development Backend | Free | Free
Afternoon | School | School | Development Backend | Development Backend | Development Backend | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-03-23 | 2015-03-24 | 2015-03-25 | 2015-03-26 | 2015-03-27 | 2015-03-28 | 2015-03-29
Morning | MS03 | School | Development UI | Development UI | Development UI | Free | Free
Afternoon | School | School | Development UI | Development UI | Development UI | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-03-30 | 2015-03-31 | 2015-04-01 | 2015-04-02 | 2015-04-03 | 2015-04-04 | 2015-04-05
Morning | Recap | School | Development UI | Development UI | Development UI | Free | Free
Afternoon | School | School | Development UI | Development UI | Development UI | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-04-06 | 2015-04-07 | 2015-04-08 | 2015-04-09 | 2015-04-10 | 2015-04-11 | 2015-04-12
Morning | Blog / MS04 | School | Write Doc | Write Doc | Write Doc | Free | Free
Afternoon | School | School | Write Doc | Write Doc | Write Doc | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-04-13 | 2015-04-14 | 2015-04-15 | 2015-04-16 | 2015-04-17 | 2015-04-18 | 2015-04-19
Morning | MS05 | School | User Testing | User Testing | MS06 | Free | Free
Afternoon | School | School | User Testing | User Testing | Reserve | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-04-20 | 2015-04-21 | 2015-04-22 | 2015-04-23 | 2015-04-24 | 2015-04-25 | 2015-04-26
Morning | Recap | School | Reserve | Reserve | Reserve | Free | Free
Afternoon | School | School | Reserve | Reserve | Reserve | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-04-27 | 2015-04-28 | 2015-04-29 | 2015-04-30 | 2015-05-01 | 2015-05-02 | 2015-05-03
Morning | Blog | School | Prototype / MS07 | Write BA | Write BA | Free | Free
Afternoon | School | School | Prototype / MS07 | Write BA | Write BA | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-05-04 | 2015-05-05 | 2015-05-06 | 2015-05-07 | 2015-05-08 | 2015-05-09 | 2015-05-10
Morning | Recap | School | Write BA | Write BA | Write BA | Free | Free
Afternoon | School | School | Write BA | Write BA | Write BA | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-05-11 | 2015-05-12 | 2015-05-13 | 2015-05-14 | 2015-05-15 | 2015-05-16 | 2015-05-17
Morning | Recap | School | Write BA | Write BA | Write BA | Free | Free
Afternoon | School | School | Write BA | Write BA | Write BA | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-05-18 | 2015-05-19 | 2015-05-20 | 2015-05-21 | 2015-05-22 | 2015-05-23 | 2015-05-24
Morning | Blog | School | Review | Review | Abgabe BA!!! MS08 | Free | Free
Afternoon | School | School | Review | Review | Abgabe BA!!! MS08 | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-05-25 | 2015-05-26 | 2015-05-27 | 2015-05-28 | 2015-05-29 | 2015-05-30 | 2015-05-31
Morning | Abstract | School | Abstract | Abstract | Create Presentation | Free | Free
Afternoon | School | School | Abstract | Abstract | Create Presentation | Free | Free
Day | Montag | Dienstag | Mittwoch | Donnerstag | Freitag | Samstag | Sonntag
Date | 2015-06-01 | 2015-06-02 | 2015-06-03 | 2015-06-04 | 2015-06-05 | 2015-06-06 | 2015-06-07
Morning |  | School | Prepare Presentation | Prepare Presentation | Upload Abstract on Moodle / MS09 | Free | Free
Afternoon | School | School | Prepare Presentation | Prepare Presentation | Upload Abstract on Moodle / MS09 | Free | Free
Note on F4: Renato Stauffer: What does already exist? How are those solutions implemented?
Note on D12: Renato Stauffer: Rreview different tools and opportunities